## general_report
SEF Jira
Displaying 94 issues at 26/Aug/16 6:48 PM.
Project | Key | Summary | Issue Type | Status | Priority | Reporter | Creator | Created | Last Viewed | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Description
IFB299 2016-Sem2 110 | SRCX-94 | SRCX-17 Deploy to Production Server | Sub-task | Open | Must Have | Thanh - Ha Nguyen | Thanh - Ha Nguyen | 2016-08-26 10:32 | 2016-08-26 18:48 | 3600 | 3600 |  | 0%
IFB299 2016-Sem2 110 | SRCX-93 | SRCX-17 Mockup Online Order Page Design | Sub-task | Open | Must Have | Thanh - Ha Nguyen | Thanh - Ha Nguyen | 2016-08-26 10:31 | 2016-08-26 18:36 | 10800 | 10800 |  | 0%
IFB299 2016-Sem2 110 | SRCX-92 | SRCX-17 Design Database Schema For Order Table | Sub-task | Open | Must Have | Thanh - Ha Nguyen | Thanh - Ha Nguyen | 2016-08-26 10:31 | 2016-08-26 18:31 | 7200 | 7200 |  | 0%
IFB299 2016-Sem2 110 | SRCX-91 | SRCX-9 Deploy to Server and Run Production Migrations | Sub-task | Open | Must Have | Amos Fox | Amos Fox | 2016-08-26 10:23 | 2016-08-26 18:38 | 3600 | 3600 |  | 0% |  | Deploy development to production and re-run migration files to build database on production server
IFB299 2016-Sem2 110 | SRCX-90 | SRCX-36 Deploy to Production Server | Sub-task | Open | Must Have | Amos Fox | Amos Fox | 2016-08-26 10:21 | 2016-08-26 18:28 | 3600 | 3600 |  | 0%
IFB299 2016-Sem2 110 | SRCX-89 | SRCX-16 Deploy to Production Server | Sub-task | Open | Must Have | Thanh - Ha Nguyen | Thanh - Ha Nguyen | 2016-08-26 10:12 | 2016-08-26 18:23 | 3600 | 3600 |  | 0%
IFB299 2016-Sem2 110 | SRCX-88 | SRCX-36 Mockup Login Page Design | Sub-task | Open | Must Have | Amos Fox | Amos Fox | 2016-08-26 10:12 | 2016-08-26 18:29 | 7200 | 7200 |  | 0% |  | Design the login page to aide the implementation phase.
IFB299 2016-Sem2 110 | SRCX-87 | SRCX-16 Mockup Customer Account Create Page Design | Sub-task | Open | Must Have | Thanh - Ha Nguyen | Thanh - Ha Nguyen | 2016-08-26 10:09 | 2016-08-26 18:25 | 10800 | 10800 |  | 0% |  | Customer Account page design
IFB299 2016-Sem2 110 | SRCX-86 | SRCX-35 Deploy to Production Server | Sub-task | Open | Must Have | Amos Fox | Amos Fox | 2016-08-26 10:09 | 2016-08-26 18:20 | 3600 | 3600 |  | 0% |  | Deploy the development build to the production server
IFB299 2016-Sem2 110 | SRCX-85 | SRCX-16 Design Database Schema For Customers Table | Sub-task | Open | Must Have | Thanh - Ha Nguyen | Thanh - Ha Nguyen | 2016-08-26 10:08 | 2016-08-26 18:21 | 7200 | 7200 |  | 0% |  | Designing plan of a database for Customers Table
IFB299 2016-Sem2 110 | SRCX-84 | SRCX-35 Setup Deployment Server | Sub-task | Open | Must Have | Amos Fox | Amos Fox | 2016-08-26 10:08 | 2016-08-26 18:16 | 7200 | 7200 |  | 0%
IFB299 2016-Sem2 110 | SRCX-83 | SRCX-35 Mockup Home Page Design | Sub-task | Open | Must Have | Amos Fox | Amos Fox | 2016-08-26 10:06 | 2016-08-26 18:18 | 7200 | 7200 |  | 0% |  | Mockup the page design to aide in the implementation
IFB299 2016-Sem2 110 | SRCX-82 | SRCX-35 Create Local Repository and Remote and add developers to group | Sub-task | Open | Must Have | Amos Fox | Amos Fox | 2016-08-26 10:03 | 2016-08-26 18:19 | 3600 | 3600 |  | 0% |  | Create Repository and remote repo, add and configure developers
IFB299 2016-Sem2 110 | SRCX-81 | SRCX-9 User Acceptance Criteria | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:52 |  | 3600 | 3600 |  | 0% |  | - The user is unable to create multiple orders with the same order ID
IFB299 2016-Sem2 110 | SRCX-80 | SRCX-9 Write Test Cases | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:51 | 2016-08-26 18:38 | 7200 | 7200 |  | 0% |  | Write test cases to cover the following: - Create duplicate order - Create normal order
IFB299 2016-Sem2 110 | SRCX-79 | SRCX-17 User Acceptance Criteria | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:46 |  | 7200 | 7200 |  | 0% |  | - Online Order Page available to customers who are logged in - Links to page provided in navigation bar - Page contains form where customer can submit details relevant to the order - User input is validated before order confirmation - Customer receives confirmation of order after submitting
IFB299 2016-Sem2 110 | SRCX-78 | SRCX-17 Refine Auto-Generated Online Order Form | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:44 |  | 7200 | 7200 |  | 0% |  | Format the automatically generated online order form to conform to the design standards of the rest of the page.
IFB299 2016-Sem2 110 | SRCX-77 | SRCX-17 Write Test Cases | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:42 |  | 7200 | 7200 |  | 0% |  | Write test cases for the following items: - Order Creation (valid) - Order Creation (invalid) - Order presence in database - Validation for formatting and presence of all fields
IFB299 2016-Sem2 110 | SRCX-76 | SRCX-17 Input Validation | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:40 |  | 7200 | 7200 |  | 0% |  | Validate all form inputs and check for formatting and presence.
IFB299 2016-Sem2 110 | SRCX-75 | SRCX-36 User Acceptance Criteria | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:35 | 2016-08-26 18:28 | 7200 | 7200 |  | 0% |  | - Login Page accessable from navigation bar - Login page with form that prompts the user for an email and password - Validate presence of given email in database - Validation of user credentials through password authentication - Upon successful login, session is created
IFB299 2016-Sem2 110 | SRCX-74 | SRCX-36 Write Test Cases | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:34 | 2016-08-26 18:28 | 7200 | 7200 |  | 0% |  | Write Test Cases which test: - Encrypted Password - Correct Login - Incorrect Login
IFB299 2016-Sem2 110 | SRCX-73 | SRCX-16 User Acceptance Criteria | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:25 | 2016-08-26 18:24 | 7200 | 7200 |  | 0% |  | - Customer is prompted to provide the following information: Username, First Name, Last Name, Card Number, Card Type (Visa, Mastercard), CCV, Expiry Date, Street, Suburb, Postcode, City, Email Address, Password - All the above fields are validated to check formatting and to ensure none are empty, email is checked for uniqueness as two users cannot share the same email.
IFB299 2016-Sem2 110 | SRCX-72 | SRCX-16 Input Validation of Customers Table | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:24 |  | 7200 | 7200 |  | 0% |  | Add validation to the fields inputted into the database table. This includes missing, non-unique, wrong-format information.
IFB299 2016-Sem2 110 | SRCX-71 | SRCX-16 Write Test Cases | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:22 | 2016-08-26 18:25 | 7200 | 7200 |  | 0% |  | Write test cases for the following items: - Database Access - Input Validation (empty, uniqueness, wrong format) etc.
IFB299 2016-Sem2 110 | SRCX-70 | SRCX-35 Create Home Page Banner and Main Content | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:17 | 2016-08-26 18:17 | 3600 | 3600 |  | 0% |  | Fill the created view with the banner and description content
IFB299 2016-Sem2 110 | SRCX-69 | SRCX-35 Create Navigation Bar Partial | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:16 | 2016-08-26 18:17 | 3600 | 3600 |  | 0% |  | Create a navigation bar partial and place a reference to it in the application.html.erb file.
IFB299 2016-Sem2 110 | SRCX-68 | SRCX-35 User Acceptance Criteria | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-22 11:15 | 2016-08-26 18:17 | 3600 | 3600 |  | 0% |  | - Home page viewable upon navigation to root of web solution - Provides Navigation bar with placeholder links to other locations - Contains banner which states the purpose of the website
IFB299 2016-Sem2 110 | SRCX-67 | SRCX-28 Copy Existing Frequent Questions into Webpage | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-20 14:01 |  | 900 | 900 |  | 0% |  | Copy the Frequently Asked Questions provided by the client into the webpage.
IFB299 2016-Sem2 110 | SRCX-66 | SRCX-28 Create and Style View | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-20 14:00 |  | 3600 | 3600 |  | 0% |  | Create and Style the FAQ page using HTML and CSS
IFB299 2016-Sem2 110 | SRCX-65 | SRCX-28 Create Route and add page to Existing Pages Controller | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-20 13:59 |  | 600 | 600 |  | 0% |  | Create route to the FAQ page in the routes file
IFB299 2016-Sem2 110 | SRCX-64 | SRCX-37 Create and Style View | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-20 13:55 |  | 3600 | 3600 |  | 0% |  | Create and Style the About webpage using HTML and CSS
IFB299 2016-Sem2 110 | SRCX-63 | SRCX-37 Create Route and add page to Existing Pages Controller | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-20 13:54 |  | 600 | 600 |  | 0% |  | Create route to About Page and add to Existing Pages Controller
IFB299 2016-Sem2 110 | SRCX-62 | SRCX-25 Create and Style View | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-20 13:49 |  | 3600 | 3600 |  | 0% |  | Create and Style the webpage using HTML and CSS
IFB299 2016-Sem2 110 | SRCX-61 | SRCX-25 Create Route and add page to Existing Pages Controller | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-20 13:49 |  | 600 | 600 |  | 0% |  | Create the route in the routes file and add to controller
IFB299 2016-Sem2 110 | SRCX-60 | SRCX-31 Create Migration file to Modify Customers Table | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-20 13:41 |  | 900 | 900 |  | 0% |  | Add a password digest field to the Customers Database through a migration file then migrate it.
IFB299 2016-Sem2 110 | SRCX-59 | SRCX-31 Install Authentication Ruby Gem and Dependencies | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-20 13:40 |  | 1200 | 1200 |  | 0% |  | Add BCrypt to the Gemfile and download dependencies.
IFB299 2016-Sem2 110 | SRCX-58 | SRCX-9 Primary Key Constraint Scaffolding | Sub-task | Open | Major | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:30 |  | 3600 | 3600 |  | 0% |  | Ensure that upon creation of the scaffold for the orders table, an auto-incrementing identification value is created.
IFB299 2016-Sem2 110 | SRCX-57 | SRCX-17 Create and Style View | Sub-task | Open | Trivial | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:28 | 2016-08-26 18:36 | 14400 | 14400 |  | 0% |  | Modify the generated view to fit the styling of the rest of the site.
IFB299 2016-Sem2 110 | SRCX-56 | SRCX-17 Migrate Database Scaffolding | Sub-task | Open | Major | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:27 |  | 3600 | 3600 |  | 0% |  | Migrate the scaffolding for the orders table to create a schema and required Views, Models, Controllers.
IFB299 2016-Sem2 110 | SRCX-55 | SRCX-17 Generate Database Scaffolding for Orders Table | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:26 |  | 3600 | 3600 |  | 0% |  | Create the database scaffolding which will create the fields required for order creation.
IFB299 2016-Sem2 110 | SRCX-54 | SRCX-16 Refine Auto-Generated Customer Account Form | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:24 | 2016-08-26 18:24 | 10800 | 10800 |  | 0% |  | Tailor the automatically generated customer registration form to fit in with the rest of the page.
IFB299 2016-Sem2 110 | SRCX-53 | SRCX-36 Create and Style Login Page View | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:22 | 2016-08-26 18:29 | 7200 | 7200 |  | 0% |  | Create the Login page view and style it appropriately.
IFB299 2016-Sem2 110 | SRCX-52 | SRCX-36 Creation of Login Form | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:20 | 2016-08-26 18:28 | 7200 | 7200 |  | 0% |  | Create the login form which accepts the users credentials
IFB299 2016-Sem2 110 | SRCX-51 | SRCX-36 Create Sessions Controller | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:16 | 2016-08-26 18:29 | 3600 | 3600 |  | 0% |  | Create the sessions controller which will handle the session management for the login functionality. This includes comparison of the given password with the hash and user email validation
IFB299 2016-Sem2 110 | SRCX-50 | SRCX-35 Create Home Page View | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:14 | 2016-08-26 18:17 | 3600 | 3600 |  | 0% |  | Complete HTML and CSS Styling required for the homepage
IFB299 2016-Sem2 110 | SRCX-49 | SRCX-35 Create Controller for Home Page to handle route | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:14 | 2016-08-26 18:18 | 3600 | 3600 |  | 0% |  | Create Controller for Home Page to handle route
IFB299 2016-Sem2 110 | SRCX-48 | SRCX-35 Add Home Page route to routing file | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 12:13 |  | 3600 | 3600 |  | 0% |  | Add home page route to routing file
IFB299 2016-Sem2 110 | SRCX-47 | Edit Quote Prices | Story | Open | Should Have | Amos Fox | Amos Fox | 2016-08-19 10:46 | [6 empty] | As an operator, I would like the ability to edit the pricing structure for the quoting of the package delivery form, to remain competitive in the courier industry.
IFB299 2016-Sem2 110 | SRCX-46 | SRCX-16 Create and Style View | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 10:44 | 2016-08-26 18:25 | 14400 | 14400 |  | 0% |  | Create and style the HTML for the view.
IFB299 2016-Sem2 110 | SRCX-45 | SRCX-16 Create Controller | Sub-task | Open | Trivial | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 10:42 |  | 3600 | 3600 |  | 0% |  | Create customers controller for database and view
IFB299 2016-Sem2 110 | SRCX-44 | SRCX-16 Database Migration | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 10:40 | 2016-08-26 18:29 | 3600 | 3600 |  | 0% |  | Migrate the scaffold migration file to generate a schema
IFB299 2016-Sem2 110 | SRCX-43 | SRCX-16 Database Scaffolding | Sub-task | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-19 10:38 |  | 3600 | 3600 |  | 0% |  | Build scaffolding for database Customers table
IFB299 2016-Sem2 110 | SRCX-42 | Operator Management Page | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-18 19:10 | 2016-08-26 18:12 | [5 empty] | As a operator, I require a dashboard that provides me with links to required functionality. This will allow me to quickly access and complete a certain task. Acceptance Criteria: - Web page should be able to provide navigation to the orders list - Web page should provide space to allow the addition of other features in the future - Access restricted to operators only
IFB299 2016-Sem2 110 | SRCX-41 | View Current Orders and Status | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-18 19:07 | 2016-08-26 18:12 | [5 empty] | As an Operator, I require the ability to view all orders that are moving through my company and their associated status
IFB299 2016-Sem2 110 | SRCX-40 | Operator Login Page | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-18 19:03 | 2016-08-26 18:12 | [5 empty] | As an Operator, I require the ability to login to my online management page so that I can perform my required tasks.
IFB299 2016-Sem2 110 | SRCX-39 | Driver Management login page | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-18 18:53 | 2016-08-26 18:11 | [5 empty] | As a driver, I require the ability to login into my management page so that my day-to-day operations are protected Acceptance Criteria: - Require login form with link from navigation page
IFB299 2016-Sem2 110 | SRCX-38 | Driver Management Page | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-18 18:51 | 2016-08-26 18:11 | [5 empty] | As a driver, I require a management page which provides links to the various form I need to complete during a delivery.
IFB299 2016-Sem2 110 | SRCX-37 | Company About Page | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-18 18:38 | 2016-08-26 18:10 |  |  |  |  | SRCX-63, SRCX-64 | As a business operator, I would like to be able to describe my business and its services through a dedicated page on the website. Acceptance Criteria: - Individual, static about page with link from navigation area
IFB299 2016-Sem2 110 | SRCX-36 | Customer Login Page | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-18 18:30 | 2016-08-26 18:29 |  |  |  |  | SRCX-51, SRCX-52, SRCX-53, SRCX-74, SRCX-75, SRCX-88, SRCX-90 | As a customer, I require the ability to log into my account so that I can then place orders.
IFB299 2016-Sem2 110 | SRCX-35 | Company Home Page | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-18 18:27 | 2016-08-26 18:20 |  |  |  |  | SRCX-48, SRCX-49, SRCX-50, SRCX-68, SRCX-69, SRCX-70, SRCX-82, SRCX-83, SRCX-84, SRCX-86 | As an operator, I require a home page which will provide my company a web presence.
IFB299 2016-Sem2 110 | SRCX-34 | Package Insurance | Story | Open | Won't Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-17 12:47 | [6 empty] | As a customer, I would like to be able to organise insurance for my package through the order form if I deem it appropriate. So that I will have peace of mind.
IFB299 2016-Sem2 110 | SRCX-33 | Automated Route Calculation | Story | Open | Won't Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-17 12:41 | 2016-08-26 18:15 | [5 empty] | As an operator, I would like the ability for the system to calculate the most efficient routes for each driver so that time and fuel are saved.
IFB299 2016-Sem2 110 | SRCX-32 | Driver Geo-Location Tracking | Story | Open | Won't Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-17 12:40 | 2016-08-26 18:15 | [5 empty] | As a customer, I would like to be able to track the driver who is delivering my package in real time so that I can be more wary as to when it'll arrive.
IFB299 2016-Sem2 110 | SRCX-31 | Encrypted Customer Password | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-17 12:20 | 2016-08-26 18:10 |  |  |  |  | SRCX-59, SRCX-60 | As a customer, I would like my password to be encrypted in the database to ensure my account is protected.
IFB299 2016-Sem2 110 | SRCX-30 | Responsive Site Design | Story | Open | Could Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 17:01 | [6 empty] | As a customer, I would like the website to be responsive, so that I can access it easily accross multiple devices.
IFB299 2016-Sem2 110 | SRCX-29 | Request Re-delivery of Package | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 17:01 | 2016-08-26 18:13 | [5 empty] | As a customer, I would like the ability to request the re-delivery of an order if I miss the delivery driver. Acceptance Criteria: - A page available from the navigation menu that allows the customer to type in the unique package ID to organise redelivery
IFB299 2016-Sem2 110 | SRCX-28 | Customer FAQ Page | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 17:00 | 2016-08-26 18:10 |  |  |  |  | SRCX-65, SRCX-66, SRCX-67 | As a customer, I would like to view frequently asked questions so that I don't have to seek further contact if my query has already been answered. Acceptance Criteria: - A static page with FAQ's with a hyperlink from the navigation menu
IFB299 2016-Sem2 110 | SRCX-27 | Special Delivery Orders | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 16:58 | 2016-08-26 18:12 | [5 empty] | As a customer, I would like to be able to include special instructions upon order creation for the driver if the pickup location requires special access etc. Acceptance Criteria: - A text box during the order creation process that allows the customer to enter specific instructions to the driver
IFB299 2016-Sem2 110 | SRCX-26 | Customer Order History | Story | Open | Could Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 16:57 | 2016-08-26 18:13 | [5 empty] | As a customer, I require the ability to view my order history, along with details of each order. Acceptance Criteria: - A page containing a table with information of deliveries associated with the customer account - Only accessible while logged in
IFB299 2016-Sem2 110 | SRCX-25 | Business Contact Information | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 16:56 | 2016-08-26 18:10 |  |  |  |  | SRCX-61, SRCX-62 | As a customer, I would like to view contact information about the company such as phone number so that I can contact the owner directly. Acceptance Criteria: - Static page available as a hyperlink from the navigation menu with contact information
IFB299 2016-Sem2 110 | SRCX-24 | Customer Favorite Recipients | Story | Open | Could Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 16:56 | 2016-08-26 18:14 | [5 empty] | As a customer, I would like to be able to save a list of favorite recipients so that repeated orders to the same address are quicker. Acceptance Criteria: - A form that the customer can fill out with the addresses of regular contacts - Only accessible while customer is logged in - During the order creation, this appears in a drop down menu to pre-populate the order form
IFB299 2016-Sem2 110 | SRCX-23 | Customer Account Information Change | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 16:54 | 2016-08-26 18:14 | [5 empty] | As a customer, I would like the ability to be able to edit my account information in order to keep my records current. - Online form that can be filled out with updated address and account information - Can only be accessed once customer has logged in
IFB299 2016-Sem2 110 | SRCX-22 | Customer Passord Reset | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 16:53 | [6 empty] | As a customer, I require the ability to reset my password in case I forget it so that I can quickly re-access my account. Acceptance Criteria: * A button labelled "reset password" button which links to another form where user can enter an email address and receive a link to reset their password. * From this link, the customer can then enter in a new password which will overwrite their old one in the database.
IFB299 2016-Sem2 110 | SRCX-21 | Driver Pickup Form | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 16:51 | 2016-08-26 18:11 | [5 empty] | As a driver, I require the ability to submit information about an order upon pickup, such as whether the order was paid or not and the number of packages in the order. Acceptance Criteria: * Form where driver can input various details about order post-delivery
IFB299 2016-Sem2 110 | SRCX-20 | Log Driver Mileage | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 16:50 | 2016-08-26 18:15 | [5 empty] | As a driver, I would like to be able to log the number of km's travelled each day in order to help the operator optimise routes. Acceptance Criteria: * Form where driver can input total Kilometers traveled each day
IFB299 2016-Sem2 110 | SRCX-19 | Driver Roster | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-12 16:47 | 2016-08-26 18:14 | [5 empty] | As an operator, I would like to be able to view the days in which each driver is rostered to aid in the planning of pickups and deliveries. Acceptance Criteria: * List of drivers and their availabilities, formatted as table * Only viewable by operator
IFB299 2016-Sem2 110 | SRCX-18 | Payment information access | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 20:07 | 2016-08-26 18:12 | [5 empty] | As the business operator, I require the ability to view payment information of customer orders so that I can charge them for the service. Acceptance Criteria: * Business operator can view details about unpaid orders
IFB299 2016-Sem2 110 | SRCX-17 | Online order submission | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 20:06 | 2016-08-26 18:37 |  |  |  |  | SRCX-55, SRCX-56, SRCX-57, SRCX-76, SRCX-77, SRCX-78, SRCX-79, SRCX-92, SRCX-93, SRCX-94 | As a customer, I would like to be able to place an order online through filling out an online form.
IFB299 2016-Sem2 110 | SRCX-16 | Customer account creation | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 20:05 | 2016-08-26 18:25 |  |  |  |  | SRCX-43, SRCX-44, SRCX-45, SRCX-46, SRCX-54, SRCX-71, SRCX-72, SRCX-73, SRCX-85, SRCX-87, SRCX-89 | As a customer, I would like the ability to create an account to allow me to place orders through the online system.
IFB299 2016-Sem2 110 | SRCX-15 | Mark orders as 'Complete' | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 20:03 | 2016-08-26 18:14 | [5 empty] | As a driver I want to be able to update the order status to complete so that the customers and operators can keep track of packages. Acceptance criteria: - front-end interface to update order status of given order id - back end database to perform and store operation
IFB299 2016-Sem2 110 | SRCX-14 | Package warehouse arrival record | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 20:02 | 2016-08-26 18:11 | [5 empty] | As a driver, I need to record when a package arrives at the warehouse so customers and management can follow the progress of orders. Acceptance criteria: - front end input form to allow driver to check-in package - corresponding database to store value
IFB299 2016-Sem2 110 | SRCX-13 | Signature collection on delivery | Story | Open | Could Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:59 | [6 empty] | As a delivery driver, I would like a way to collect a signature from the recipient as a means of verifying the identity of the receiver. Acceptance criteria: - front end software to accept image upload of signature-device - back end database field to store information
IFB299 2016-Sem2 110 | SRCX-12 | Service range index | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:57 | 2016-08-26 18:14 | [5 empty] | As a business operator, I would like to be able to maintain a record of post codes that my company can service in order to be able to determine cost and serviceability of incoming orders. Acceptance criteria: - front end form to accept post code input field - database table that stores postcode field corresponding to customer
IFB299 2016-Sem2 110 | SRCX-11 | Driver site form submission | Story | Open | Could Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:53 | [6 empty] | As a driver, I would like the functionality to submit order details such as payment on package pickup to allow orders to be processed quicker and lift responsibility from the operator to the driver. Acceptance criteria: - Front end form to receive input from driver - Corresponding database table to accept information - Information must be linked via order number primary key
IFB299 2016-Sem2 110 | SRCX-10 | Customer order tracking | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:48 | [6 empty] | As a customer I would like to track the status of my order throughout the delivery process so that I am more informed as to when the recipient will receive it. Acceptance criteria: - Requires a check-in field in each database table to track which stage the package is at in the process - Front-end display of information is required that logically expresses this information to the user in an abstracted form.
IFB299 2016-Sem2 110 | SRCX-9 | Unique identifier for orders | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:47 | 2016-08-26 18:37 |  |  |  |  | SRCX-58, SRCX-80, SRCX-81, SRCX-91 | As an operator, I want the ability to assign an identification number so I can track orders within the company.
IFB299 2016-Sem2 110 | SRCX-8 | Manage employed drivers | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:45 | [6 empty] | As a business operator, I want to add and remove employed drivers to keep my records current. Acceptance criteria: - Must have software to access database records. - Must be straightforward software to use.
IFB299 2016-Sem2 110 | SRCX-7 | CRUD operations on customer records | Story | Open | Must Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:43 | [6 empty] | As an operator, I need to maintain (add, modify, remove) customer records so that I can keep the records updated and relevant. Acceptance criteria: - front end software to access the database - front end software must be straight forward to use.
IFB299 2016-Sem2 110 | SRCX-6 | Generating business-related statistics | Story | Open | Could Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:40 | [6 empty] | As a business operator, I want to access statistics that reflect the performance of my delivery drivers and incoming orders to allow me to monitor the profitability of my business. Acceptance criteria: - System that logs drivers activities and orders. - Gathers routes of drivers through GPS. - Collects information periodically.
IFB299 2016-Sem2 110 | SRCX-5 | Verification of delivery address | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:38 | [6 empty] | As a customer, I would like the ability to verify that my inputted address is correct before committing to an order. Acceptance criteria: - Has a page before the order is processed displaying all entered information. - Has an option to edit details while on this confirmation page.
IFB299 2016-Sem2 110 | SRCX-4 | Alternative delivery options | Story | Open | Could Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:36 | [6 empty] | As a customer, if the company is unable to deliver to my area, I would like to view alternative delivery companies that can service my area. Acceptance criteria: - Must have hyperlinks to other courier services after an address is entered in an area that is not serviced.
IFB299 2016-Sem2 110 | SRCX-3 | User feedback collection | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:33 | [6 empty] | As a customer, I would like to rate the service and provide written feedback about it so the service can be improved. Acceptance criteria: - automatically send email to user immediately after delivery requesting feedback and rating
IFB299 2016-Sem2 110 | SRCX-2 | Delivery quoting functionality | Story | Open | Should Have | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:31 | [6 empty] | As a customer, I would like to be able to request a quote on the cost of my package before committing to an order. Acceptance criteria: - Have a form requesting details of client/package - Have a program to calculate values based on input from form - Generate unique code to take up quoted price at a later time
IFB299 2016-Sem2 110 | SRCX-1 | test issue | Story | Closed | Trivial | Michael Leontieff - Smith | Michael Leontieff - Smith | 2016-08-08 19:20
Generated at Fri Aug 26 18:48:32 EST 2016 by Michael Leontieff - Smith using JIRA 6.2.7#6265-sha1:91604a8de81892a3e362e0afee505432f29579b0.